## Bug Report Template
S/N | APP | Module | Observation | Steps to Reproduce | Recommendation | Priority | Development Status | Assignee | Release Version | Testing Version | Testing Status | Comments/Screenshots | Tester
1 | Website | Data Entry | Data values disappear after clicking "Save" in the Immunization Dataset for July 2025. No error shown. | 1. Log in to DHIS2 2. Go to Data Entry 3. Select Organisation Unit, Period = July 2025, and Immunization Dataset 4. Enter valid data for one or more fields 5. Click Save | Check form configuration and backend logs. Fix data persistence issue and provide user feedback on save success/failure. | High | Published | John | Beta 01 | Beta 02 | Pass | Environment: DHIS2 v2.37, Chrome v124, Server: Ubuntu 20.04 | Jane
3 | Mobile App | Login Page | Login fails when password contains special characters like @ or #. Error message shows "Invalid credentials" even when the username and password are correct. | 1. Open the Student Portal 2. Go to the Login Page 3. Enter a valid username (e.g., john.doe) 4. Enter password with special characters (e.g., Johndoe@123) 5. Click the Login button | Update the password validation logic to allow special characters and display appropriate error messages when input fails format checks. | Medium | Published | Doe | Beta 03 | Beta 02 | Failed | Environment: Chrome v114, Windows 10 | Roe
[6 empty] | Medium | Pending | Julius
[6 empty] | High | Published | Eric